## Natural Areas
Vuln. Number | Vulnerability | Action Number | Action | Action Type | Process | Possible Actors
NA1 | INFO: There is a limited understanding of how tidal marshes and mudflats, and adjacent upland ecotone habitats and subtidal habitats, will respond to accelerating sea level rise, how these habitats will be affected by management actions to increase sediment supply or provide transition zone habitat to support upland migration, or how they will respond to shoreline adaptation measures. | NA1.1 | Establish an early detection system to monitor tidal marsh elevation trends relative to sea level rise, i.e., identify when marshes are approaching key thresholds/triggers for management decisions, e.g., measure vertical accretion, observe changes in vegetation and indicator species, document marsh edge erosion (photo-points/surveys) | Program/operation | Long-range Planning, Operations | EBRPD, SCC, DFW, BCDC, RWQCB, USFWS, NOAA, SFBRA, SFEP, SF Bay NERR
|  | NA1.2 | Research and pilot test management actions that will improve tidal marsh resilience, including new or innovative measures to increase marsh sediment supply, encourage vertical accretion and upland migration, or reduce marsh edge erosion (e.g., oyster and eelgrass reefs and other offshore habitats that can act as wave breaks) | Program/operation | Capital Planning | EBRPD, CCCFCWCD, SCC, DFW, BCDC, RWQCB, USACE, USFWS, FEMA, City, County, CBOs, Private Entities, SFBRA
|  | NA1.3 | Support the development of a comprehensive regional sediment management plan that emphasizes the reuse of suitable sediment for baylands enhancement and restoration | Policy Development, Program/operation | Long-range Planning | EBRPD, CCCFCWCD, SCC, DFW, BCDC, RWQCB, USACE, USFWS, FEMA, City, County, CBOs, Private Entities, SFBRA
|  | NA1.3 | Support a regional research agenda to advance the understanding of how tidal marsh and adjacent ecotone and subtidal habitats will be affected by different shoreline adaptation responses (e.g., structural solutions such as levees; natural solutions such as living shorelines) that may change tide, wave or sediment conditions in marshes | Evaluation | Project Planning and Design | EBRPD, CCCFCWCD, SCC, DFW, BCDC, RWQCB, USACE, USFWS, FEMA, City, County, CBOs, Private Entities, SFBRA, USGS, SFEP, SFEI, UC Berkeley, SFEI
NA2 | GOV1: Proactive management of tidal marshes, mudflats, adjacent upland ecotone habitats and subtidal habitats to improve resilience to sea level rise and storm events will require review and authorization from multiple local, state and federal agencies, which can be cumbersome and time consuming and often results in limited work windows and/or restrictions on the types of actions that can be taken. | NA2.1 | Research and pilot test different approaches to implementing tidal marsh resilience actions (e.g. restoration, transition habitat, active revegetation, high tide refuge islands, or living shoreline) to identify best practices for avoiding impacts to species, water quality, or other natural resource values | Program/operation | Capital Planning | EBRPD, CCCFCWCD, SCC, DFW, BCDC, RWQCB, USACE, USFWS, FEMA, City, County, CBOs, Private Entities, SFBRA
|  | NA2.2 | Develop and implement a regional program to expedite permit review and approval and coordinate monitoring and mitigation requirements of restoration and enhancement projects that proactively improve resilience of tidal marsh, mudflat, adjacent upland ecotone and subtidal habitats to sea level rise | Policy Development, Program/operation | New Initiative | EBRPD, CCCFCWCD, SCC, DFW, BCDC, RWQCB, USACE, USFWS, FEMA, City, County, CBOs, Private Entities, SFBRA
NA3 | GOV2: Marsh restoration and enhancement projects that include railroad tracks, highways, pipelines, PG&E towers, etc. require additional approvals and coordination | NA3.1 | Develop a collaborative process for planning, permitting and implementing multi-objective projects that improve both tidal marsh and infrastructure resilience where these built and natural systems are co-located | Policy Development, Program/operation | New Initiative | EBRPD, CCCFCWCD, SCC, DFW, BCDC, RWQCB, USACE, USFWS, FEMA, City, County, CBOs, Private Entities, SFBRA
NA4 | GOV3: The prevailing model of fragmented decision-making, existing natural resources laws, and a history of passive management limits the ability to advance innovative or untested marsh restoration and enhancement actions and nature-based shoreline resilience solutions | NA4.1 | Participate in collaborative regional discussions to explore where legal, policy or regulatory changes are needed to promote nature-based solutions, such as constructing oyster and eelgrass reefs in a living shorelines approach, to address existing and future infrastructure adaptation challenges | Policy Development, Program/operation | New Initiative | EBRPD, CCCFCWCD, SCC, DFW, BCDC, RWQCB, USACE, USFWS, FEMA, City, County, CBOs, Private Entities, SFBRA, SFEP
|  | NA4.2 | Develop a decision-making framework for planning and implementing resilient, multi-objective shoreline adaptation projects that clearly weigh the trade-offs among short and long term impacts versus benefits to the economy, environment and social equity | Policy Development | New Initiative | EBRPD, CCCFCWCD, SCC, DFW, BCDC, RWQCB, USACE, USFWS, FEMA, City, County, CBOs, Private Entities, SFBRA, SFEP
|  | NA4.3 | Improve coordination among regulatory and planning agencies to reduce programmatic/legislative barriers and to advance the testing and implementation of nature-based solutions that will improve Bay and shoreline resilience | Policy Development, Coordination | New Initiative | EBRPD, CCCFCWCD, SCC, DFW, BCDC, RWQCB, Port, USACE, USFWS, FEMA, City, County, CBOs, Private Entities, SFBRA
NA5 | FUNC: The wildlife habitat, recreation, flood protection and other ecosystem service benefits provided by tidal marshes will not be sustained if these systems downshift to low marsh or convert to mudflat. | NA5.1 | Develop policies, guidance or incentives to encourage setbacks and buffers adjacent to tidal marshes to protect sensitive species, allow the for continued appropriate public access and recreation uses, support future marsh migration, and allow a thoughtful transition to functional subtidal habitats where possible | Policy Development | Long-range Planning, Land Use Planning | EBRPD, SCC, DFW, BCDC, State Parks, RWQCB, USFWS, NOAA, City, County, Private Entities, NPOs, CCCFCWCD, Bay Trail
|  | NA5.2 | Create, improve, or protect high tide refugia (active ecotone transition zone revegetation, high tide refuge islands, or artificial floating islands) where it is already limited and vulnerable to increased inundation and where special status species have been identified | Program/operation | Capital Planning, Project Planning and Design | EBRPD, SCC, DFW, BCDC, State Parks, USFWS, Private Entities, NPOs
|  | NA5.3 | Protect existing, or create new, corridors that facilitate the movement of birds and wildlife to viable adjacent or nearby habitats | Program/operation | Long-range Planning, Land Use Planning | EBRPD, SCC, DFW, BCDC, State Parks, USFWS, NPOs
|  | NA5.4 | Work with local entities to integrate natural resources into Hazard Mitigation Plans | Program/operation | Emergency and Hazard Planning | Cities, County, ABAG, BCDC, CalOES, FEMA, SFEP
|  | NA5.5 | Accelerate the planning, permitting, and construction of projects to enhance or restore full baylands processes and adjacent habitats | Program/operation | Capital Planning, Project Planning and Design | EBRPD, CCCFCWCD, SCC, DFW, BCDC, SFEP, RWQCB, USACE, USFWS, NOAA, SFBRA
NA6 | PHYS1: Almost all of the tidal marshes in the project area are mostly mid-marsh and predicted to drown by 2070 (depending on sea level rise rates, sediment supply, and management interventions). The marshes with more high marsh habitat now – Parchester Marsh, Whittell Marsh, Bullhead Marsh, and State Point-Mallard Island Marsh – are predicted to convert to mudflat a few decades later. | NA6.1 | Factor sea level rise into design of new tidal marsh restorations, e.g., consider marsh future capacity to build upward and move landward, look for opportunity to purchase and restore land to facilitate marsh migration, and restore tidal marsh systems in strategic areas where they are likely to survive sea-level rise by 2030 | Program/operation | Capital Planning, Project Planning and Design | EBRPD, SCC, DFW, BCDC, State Parks, USFWS, NOAA, Private Entities, NPOs
|  | NA6.2 | Factor sea level rise into ongoing management of natural areas and tidal marsh restorations to address potential higher water levels and larger waves | Program/operation | Long-range Planning, Land Use Planning | EBRPD, SCC, DFW, BCDC, State Parks, USFWS, NOAA, NPOs
NA7 | PHYS2: All of the tidal marshes except Point Pinole Southern Marsh and Whittell Marsh are bordered or constrained by development and transportation assets, such that there is no accommodation space for them to migrate landward to avoid being squeezed by a rising Bay. | NA7.1 | Using BEHGU as a guide, develop a strategic plan to acquire and conserve upland areas, and reconnect baylands to adjacent open lands, from willing landowners in order to support marsh landward migration | Policy Development | Long-range Planning, Land Use Planning | EBRPD, SCC, DFW, BCDC, State Parks, USFWS, NPOs
|  | NA7.2 | Establish rolling easements to prevent shoreline armoring that would foreclose options for the landward migration of tidal marshes | Program/operation | Long-range Planning, Land Use Planning | EBRPD, SCC, DFW, BCDC, State Parks, USFWS, NPOs
|  | NA7.3 | Test the use of offshore restoration approaches, including oyster and eelgrass reefs, to buffer and protect adjacent tidal marshes against erosion, in particular for locations where landward migration is not feasible | Program/operation | Capital Planning | EBRPD, CCCFCWCD, SCC, DFW, BCDC, RWQCB, USACE, USFWS, FEMA, City, County, CBOs, Private Entities, SFBRA